## Sheet1
Related User Story | Task Description | Initial Estimate | Amount Remaining After… |  |  |  | Assigned to:
|  |  | Week 1 | Week 2 | Week 3 | Week 4
That User Story | Refactor to support NPC | 2
| Implement NPC | 2
| Add NPC to World | 0.5
| Load NPC | 3
| NPC Movement | 4
| Implement Items | 2
| Refactor to support Items | 2
| Add Items to World | 0.5
| Add Item/NPC Interactions | 5
| Loading Items | 3
| Dynamic Map Generation | 15 |  |  |  |  | James Bridges
| Estimate Totals | 39 | 0 | 0 | 0 | 0