## Sheet1
Related User Story | Task Description | Initial Estimate | Amount Remaining After… |  |  |  | Assigned to:
|  |  | Week 1 | Week 2 | Week 3 | Week 4
That User Story | Refactor to support NPC | 1.5 |  |  |  |  | Liam
| Implement NPC | 0 |  |  |  |  | Liam
| Add NPC to World | 0 |  |  |  |  | Liam
| Load NPC | 0 |  |  |  |  | Liam
| NPC Movement | 0 |  |  |  |  | Liam
| Implement Items | 2 |  |  |  |  | Brailey
| Refactor to support Items | 2 |  |  |  |  | Brailey
| Add Items to World | 0.5 |  |  |  |  | Brailey
| Add Item/NPC Interactions | 5 |  |  |  |  | Brailey
| Loading Items | 3 |  |  |  |  | Brailey
| Dynamic Map Generation | 15 |  |  |  |  | James Bridges
| Load Locations From File | 1 |  |  |  |  | Liam
| Estimate Totals | 30 | 0 | 0 | 0 | 0