## Sheet1
Related User Story | Task Description | Initial Estimate | Amount Remaining After…
|  |  | Week 1 | Week 2 | Week 3 | Week 4
That User Story | Implement UI (fxml and codebehind) | 1.5 | 0.5
| Implement storing location information | 2 | 0
| Design world | 0.5 | 0
| Implement loading world information | 2 | 0
| Implement move action & player | 4 | 0
| UI binding to take action & update display | 3.5 | 0.5
| Prepare and make submission | 0.5 | 0
| Estimate Totals | 14 | 1 | 0 | 0 | 0